## Sheet1
ID | Identify Objects and Goals | Duration (Days) | Start | Finish
1 | Feasibility survey | 10 | 2017-02-15 | 2017-02-24
2 | Project Pre-assessments | 3 | 2017-02-13 | 2017-02-15
3 | Refferencing Research Papers | 5 | 2017-02-15 | 2017-02-19
4 | Identify Methods and Technologies | 3 | 2017-02-20 | 2017-02-22
5 | Study on Tools and Technologies | 6 | 2017-02-23 | 2017-02-28
Select Domain and Project Scope
6 | Develop work breakdown | 2 | 2017-03-01 | 2017-03-02
7 | Plan roles and Responsibilities | 2 | 2017-03-03 | 2017-03-04
8 | Project Charter- submission | 1 |  | 2017-03-06
Project Proposal
9 | Prepare Project Proposal Report | 8 | 2017-03-08 | 2017-03-15
10 | Proposal Presentation | 3 | 2017-03-18 | 2017-03-20
SRS Document
11 | Prepare SRS Document | 10 | 2017-04-14 | 2017-04-23
12 | SRS Presentation | 5 | 2017-04-24 | 2017-04-28
Design
13 | System Design | 15 | 2017-04-30 | 2017-05-14
14 | Design DB Architecture | 5 | 2017-05-04 | 2017-05-08
15 | Design demo e-commerce web site | 7 | 2017-05-04 | 2017-05-10
Development
15 | Social Media mining and Analyzing Agent | 120 | 2017-05-09 | 2017-09-10
16 | User Opinion Predictor Agent | 120 | 2017-05-09 | 2017-09-10
17 | Trend Predicting Agent | 120 | 2017-05-09 | 2017-09-10
18 | Validation Agent and Customer behavior Analyzer | 120 | 2017-05-09 | 2017-09-10
Progress Presentation I
19 | Prepare for the presentation | 2 | 2017-06-25 | 2017-06-27
20 | Progress Presentation I | 1 |  | 2017-06-27
Progress Presentation II
19 | Prepare for the presentation | 4 | 2017-09-03 | 2017-09-06
20 | Progress Presentation II | 1 |  | 2017-09-06
Implementation
21 | Implement Whole System | 15 | 2017-09-10 | 2017-09-24
22 | System Testing
Final Report
23 | Prepare Final Report (Draft) | 10 | 2017-09-25 | 2017-10-04
24 | Prepare Feedback Submission (Draft) | 5 | 2017-10-05 | 2017-10-09
Final Presentation
25 | Prepare Final Presentation | 5 | 2017-11-10 | 2017-11-14
26 | Final Presentation and Viva | 1 |  | 2017-11-20
27 | Final Report Submission (Soft bound) | 1 |  | 2017-11-16
Research Paper
28 | Prepare Research Paper | 3 | 2017-08-10 | 2017-08-12
29 | Submit the Research Paper | 1 |  | 2017-08-18
30 | Website Assessment | 1 |  | 2017-10-27